## Job Log
Job ID | Raised Date | Site | Asset ID | Asset / Location Desc. | Category | Regulation / Standard | Compliance Record ID | Description of Work | Priority | Assigned Contractor | Status | Target Completion | Actual Completion | Quoted Cost (£) | Actual Cost (£) | Invoice Reference | Certificate Received? | Compliance Updated? | Closed By | Notes

## Instructions
Instructions
HOW TO USE THE JOB LOG
RAISING A NEW JOB
1. Enter the next Job ID in column A (format: JOB-NNNN, e.g. JOB-0001, JOB-0042).
2. Enter today's date in column B (Raised Date).
3. Select the site (CITY / MFG) in column C.
4. Enter the Asset ID from the Compliance Register or Asset Register in column D (if known).
5. Enter a brief description of the asset or location in column E.
6. Select the job category in column F:
STAT = Statutory/Regulatory requirement
PPM = Planned Preventive Maintenance
REACT = Reactive (reported defect, planned response)
EMERG = Emergency (immediate safety-critical response) - row highlighted in pale red
7. If STAT, enter the regulation name in column G and the Compliance Record ID (COMP-XXXX)
from the Compliance Register in column H.
8. Enter the description of work required in column I.
9. Select priority in column J and enter the target completion date in column M.
Target date highlighted red if overdue and job is still Open or In Progress.
PROGRESSING A JOB
10. Update Status (column L) as the job progresses:
Open > In Progress > Pending Invoice > Closed
11. Enter the contractor name in column K when assigned.
12. Enter quoted cost in column O when received.
CLOSING A JOB
13. Enter actual completion date (column N) and actual cost (column P).
14. Enter invoice reference in column Q.
15. Mark Certificate Received? (column R) - Yes / No / N/A.
16. Mark Compliance Updated? (column S) - go to Compliance Register and update
the Last Completed date and Certificate Ref for the corresponding COMP record.
17. Set Status to Closed and enter your name in Closed By (column T).
JOB ID NUMBERING
Use the format JOB-NNNN with leading zeros (JOB-0001, JOB-0002 ... JOB-0999, JOB-1000).
Never reuse a Job ID. Cancelled jobs retain their ID with Status = Cancelled.
COST TRACKING
Columns O (Quoted) and P (Actual) are formatted as GBP currency.
Enter numeric values only - do not type the £ sign.
Use Excel pivot tables or the =SUMIFS formula to report spend by site, category or contractor.