## HSE Actions List
Category | Action | First Action | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | Q1 2027 | Q2 2027 | Q3 2027 | Q4 2027 | Q1 2028 | Q2 2028 | Q3 2028 | Q4 2028
Waste Water Management | Engage Yorkshire Water for waste water assessment | Q1 2026 | N
Waste Water Management | Document all current waste streams and contractors | Q1 2026 | Y
Waste Water Management | Finalise waste water solution design and costings | Q2 2026 |  | Y
Waste Water Management | Engage contractors for waste water infrastructure | Q2 2026 |  | Y
Waste Water Management | Begin waste water system installation | Q2 2026 |  | Y
Training & Competency | Create comprehensive training matrix | Q1 2026 | Y
Training & Competency | Identify all expired or missing training | Q1 2026 | Y
Training & Competency | Deliver banksman training | Q3 2026 |  |  | Y
Training & Competency | Deliver first aid at work training | Q3 2026 |  |  | Y
Training & Competency | Deliver first aid at work training refreshers | Q2 2028 | [9 empty] | Y
Training & Competency | FLT training refreshers | Q2 2027 | [5 empty] | Y |  |  | Y
Training & Competency | Deliver FLT instructor training | Q2 2028 | [9 empty] | Y
Training & Competency | Deliver emergency first aid training | Q1 2028 | [8 empty] | Y
Training & Competency | Deliver DSE training | Q3 2028 | [10 empty] | Y
Training & Competency | Deliver manual handling refresher training | Q3 2028 | [10 empty] | Y
Fire Safety | Develop fire marshal evacuation plan | Q1 2026 | N
Fire Safety | Commission fire risk assessment - 1 Toft Green | Q1 2026 | Y
Fire Safety | Complete annual fire risk assessment | Q4 2026 |  |  |  | Y
Fire Safety | Complete fire escape engineer inspection | Q4 2026 |  |  |  | Y
Fire Safety | Purchase and install additional fire extinguishers | Q3 2026 |  |  | Y
Fire Safety | Fire Extinguisher Checks | Q1 2026 | N |  |  |  | Y |  | Y |  | Y |  | Y
H&S Policy & Documentation | Complete H&S Policy with WorkNest | Q1 2026 | Y
H&S Policy & Documentation | Establish document control and version management system | Q2 2026 |  | Y
H&S Policy & Documentation | Review and update emergency procedures | Q2 2026 |  | Y
Risk Assessments & COSHH | Complete risk assessments for significant activities | Q2 2026 |  | Y
Risk Assessments & COSHH | Complete all COSHH assessments | Q2 2026 |  | Y
Risk Assessments & COSHH | Update risk assessments based on operational changes | Q2 2027 | [5 empty] | Y
NEBOSH & Competent Person | Complete NEBOSH examination | Q3 2026 |  |  | Y
NEBOSH & Competent Person | Obtain NEBOSH certificate | Q3 2026 |  |  | Y
NEBOSH & Competent Person | Formalise competent person appointment | Q3 2026 |  |  | Y
NEBOSH & Competent Person | Define interface with WorkNest for specialist support | Q3 2026 |  |  | Y
HSE Management System | Develop and document HSE management system framework | Q4 2026 |  |  |  | Y
HSE Management System | Implement weekly and monthly inspection routines | Q4 2026 |  |  |  | Y
HSE Management System | Create HSE KPI dashboard | Q4 2026 |  |  |  | Y
HSE Management System | Establish management review schedule | Q4 2026 |  |  |  | Y
HSE Management System | Establish leading indicator dashboard | Q1 2027 |  |  |  |  | Y
Compliance Monitoring & Inspections | PAT Testing | Q1 2026 | N |  |  |  | Y |  | Y |  | Y |  | Y
Compliance Monitoring & Inspections | SEMA Racking Inspection | Q3 2026 |  |  | Y
Compliance Monitoring & Inspections | Electrical Safety Inspection | Q3 2027 | [6 empty] | Y |  |  | Y
Compliance Monitoring & Inspections | Conduct biannual management reviews | Q2 2027 | [5 empty] | Y |  | Y
Occupational Health & Surveillance | Eye Tests | Q3 2026 |  |  | Y | [7 empty] | Y
Occupational Health & Surveillance | Hearing Tests | Q3 2026 |  |  | Y |  |  |  | Y |  |  |  | Y
Occupational Health & Surveillance | Complete occupational health needs assessment | Q1 2028 | [8 empty] | Y
Driver & Contractor Safety | Complete driver H&S review and implement improvements | Q1 2027 |  |  |  |  | Y
HSE Culture & Engagement | Launch near-miss reporting system with staff training | Q1 2027 |  |  |  |  | Y
HSE Culture & Engagement | Implement HSE observation program | Q2 2027 | [5 empty] | Y
HSE Culture & Engagement | Conduct comprehensive HSE culture survey | Q2 2028 | [9 empty] | Y
HSE Culture & Engagement | Analyse 3-year HSE performance trends | Q3 2028 | [10 empty] | Y
Environmental & Waste Management | Complete waste volume review and implement improvements | Q2 2028 | [9 empty] | Y
Consultancy & Strategic Reviews | WorkNest Consultancy annual review | Q4 2026 |  |  |  | Y |  |  |  | Y |  |  |  | Y
Consultancy & Strategic Reviews | Complete Year 1 management review | Q4 2026 |  |  |  | Y
Consultancy & Strategic Reviews | Identify gaps and priorities for Year 2 | Q4 2026 |  |  |  | Y
Consultancy & Strategic Reviews | Set Year 2 objectives and budget | Q4 2026 |  |  |  | Y
Consultancy & Strategic Reviews | Hold Year 2 management review | Q4 2027 | [7 empty] | Y
Consultancy & Strategic Reviews | Set Year 3 plan and priorities | Q4 2027 | [7 empty] | Y
Consultancy & Strategic Reviews | Conduct WorkNest partnership review | Q4 2028 | [11 empty] | Y
Consultancy & Strategic Reviews | Hold 3-year strategic review meeting | Q4 2028 | [11 empty] | Y
Consultancy & Strategic Reviews | Develop 2029-2031 HSE strategic plan | Q4 2028 | [11 empty] | Y

## Sheet1
Front Door
Portland
Hampton by Hilton
Fibbers
Assembly Point
Barker Lane
Toft Green
Tanner Row
POD
Emergency Evacuation Path